PROJECT VIF

The Real-Time Student Food Bridge

MILESTONE 2

Change Implementation &

Project Management

Executing the Change, Managing the Team and Delivering the Pilot

EPITECH — Capstone / Innovative Project

Lead Engineer: Rao Muhammad Mueez

Paris, France

# Table of Contents

Table of Contents	2

1. Purpose of this Document	3

2. Project-Management Methodology	3

2.1 Why Agile / Scrum	3

2.2 MoSCoW Prioritisation	3

2.3 Scrum Ceremonies (Adapted)	4

3. Team Organisation & Governance	4

3.1 Roles and Responsibilities	4

3.2 Decision-Making and Communication	5

4. Sprint Roadmap	5

4.1 Sprint 1 (Weeks 1–4) — Foundation	5

4.2 Sprint 2 (Weeks 5–8) — Core Logic	5

4.3 Sprint 3 (Weeks 9–12) — Tax Module & Polish	5

5. Pilot Rollout Plan	6

6. Risk Register (Project Delivery)	6

7. Monitoring Progress	7

7.1 Project Indicators	7

7.2 Change Indicators	7

7.3 Definition of Done	7

8. Milestone 2 Deliverables & Transition to Milestone 3	8

# 1. Purpose of this Document

Milestone 1 defined why Vif must exist, who its stakeholders are and how the project will be welcomed. Milestone 2 answers the next question: how is the change actually carried out and managed?

This document covers the project-management methodology, the team organisation and governance, the sprint roadmap, the pilot-rollout plan, the risk register and the way progress is monitored. It is the operational bridge between the strategy of Milestone 1 and the sustainability plan of Milestone 3.

# 2. Project-Management Methodology

## 2.1 Why Agile / Scrum

Vif is a four-person student project delivered under time pressure, with requirements that will evolve as bakers and students give feedback. A heavy, fixed-plan (“waterfall”) approach would be risky. The project therefore uses an Agile / Scrum-inspired methodology, adapted to the realities of a capstone team.

| Agile principle | How it is applied in Vif |
| --- | --- |
| Iterative delivery | Work is delivered in three 4-week sprints; each sprint ends with something demonstrable. |
| Working software over documentation | Each sprint produces a runnable increment; documentation supports, not replaces, the product. |
| Responding to change | The pilot generates real feedback that re-prioritises the backlog before the next sprint. |
| Close collaboration | Short, frequent check-ins keep the React Native app and FastAPI backend synchronised. |

## 2.2 MoSCoW Prioritisation

The backlog is prioritised with the MoSCoW model so that, under time pressure, the team always builds what matters most. This prioritisation is inherited from the project’s core documentation.

| Priority | Scope | Items |
| --- | --- | --- |
| Must-Have (MVP) | Without these, Vif does not function. | Student OCR verification; one-click “Pulse” posting; Karma engine (claim timer); Secure QR handshake. |
| Should-Have | Conditions for full validation. | Automated Cerfa PDF generation; hybrid pricing (donation / wholesale); interactive 1 km map. |
| Could-Have | Valuable if time allows. | In-app impact dashboard for bakers; student notifications history; multi-language support. |
| Won’t-Have (this cycle) | Explicitly out of scope for now. | Payment processing; nationwide coverage; integrations with external POS systems. |

## 2.3 Scrum Ceremonies (Adapted)

- Sprint planning — at the start of each 4-week sprint, the team selects backlog items and assigns owners.

- Weekly stand-up — a short synchronisation: what was done, what is next, what is blocked. Adapted from daily to weekly to fit student schedules.

- Sprint review / demo — at the end of each sprint, the increment is demonstrated, ideally to a pilot baker or student.

- Sprint retrospective — the team reflects on what worked and what to improve, feeding the next sprint.

# 3. Team Organisation & Governance

## 3.1 Roles and Responsibilities

The team is organised by feature group so that ownership is clear and the mobile app and backend stay aligned. The split below is taken from the project’s core documentation.

| Feature group | Description | Owner | Main technologies |
| --- | --- | --- | --- |
| Auth & Security | Student OCR ID scan and shopkeeper login. | Member A | FastAPI Security, OAuth2, Firebase |
| Core API & DB | Database schema, Pulse logic, API endpoints. | Member B | FastAPI, PostgreSQL, SQLAlchemy |
| Mobile Core | Main app UI, QR scanner, navigation. | Member C | React Native, Expo, Vision-Camera |
| Real-time & Geofence | Map integration and push notifications. | Member D | React Native Maps, WebSockets |
| Tax & Reporting | Monthly PDF generator and shop dashboard. | Member A / B | ReportLab (Python), React Native Web |

The Lead Engineer (Rao Muhammad Mueez) additionally holds cross-cutting responsibility for architecture coherence, integration between modules, and overall delivery.

## 3.2 Decision-Making and Communication

| Mechanism | Purpose |
| --- | --- |
| Shared task board (e.g. Trello / GitHub Projects) | Single visible source of truth for backlog, in-progress and done items. |
| Git branching + pull-request review | No code merges to the main branch without a second team member’s review. |
| Weekly stand-up + written summary | Keeps everyone aligned and creates a lightweight progress record. |
| Escalation to Lead Engineer | Any blocker unresolved within 48 hours is escalated for a decision. |

# 4. Sprint Roadmap

The build is organised into three four-week sprints over a twelve-week cycle. The roadmap below is consistent with the project’s technical documentation and adds the change-management activities that run in parallel.

## 4.1 Sprint 1 (Weeks 1–4) — Foundation

- Backend: set up FastAPI, PostgreSQL and basic user models.

- Frontend: set up the React Native project, authentication screens and API connectivity.

- Tax logic: define the data structure for cost-price logging.

- Change activity (Unfreeze): begin bakery identification in the pilot zone; design posters; prepare the launch event.

## 4.2 Sprint 2 (Weeks 5–8) — Core Logic

- Karma engine: build the asynchronous logic for claim timers and no-show penalties.

- Notifications: integrate Firebase to alert students when a baker posts a Flash-Gift.

- ID verification: implement the OCR pipeline for student validation.

- Change activity (Change): run baker breakfast briefings; onboard the first pilot bakeries; recruit first students.

## 4.3 Sprint 3 (Weeks 9–12) — Tax Module & Polish

- PDF engine: build the Python service that maps donation data onto the Cerfa template.

- Map UI: implement the pulsing 1 km map in React Native.

- QR system: finalise the secure scan-to-claim flow.

- Change activity (Refreeze): deliver first monthly impact reports to pilot bakers; collect feedback; prepare the jury demo.

Parallel tracks Two tracks run in parallel throughout the twelve weeks: a build track (the software) and a change track (recruiting bakeries and students, communication, events). Milestone 2 manages both. A pilot is only meaningful if there are real bakeries and real students ready when the software is.

# 5. Pilot Rollout Plan

Vif is not launched everywhere at once. It is rolled out as a controlled pilot in a single, dense zone — ideally one Paris neighbourhood with several bakeries and a nearby campus. This limits risk, concentrates supply and demand, and produces clean feedback.

| Pilot phase | Goal | Exit criterion |
| --- | --- | --- |
| Phase 0 — Preparation | Sign the convention with the partner association; recruit 3–5 pioneer bakeries. | Legal agreement signed; pioneers committed. |
| Phase 1 — Closed pilot | Test the full flow with pioneers and a small group of student ambassadors. | End-to-end donation (Pulse → claim → QR → Cerfa record) works reliably. |
| Phase 2 — Open pilot | Open to all students in the zone; add more bakeries. | Stable daily usage; positive baker and student feedback. |
| Phase 3 — Review | Measure results; decide on scaling (handed to Milestone 3). | Pilot report produced; go / no-go decision made. |

# 6. Risk Register (Project Delivery)

This register covers risks to delivering the project on time and to quality. Adoption risks are in Milestone 1; security risks are in the Threat Model. Each risk is rated by likelihood (L) and impact (I) on a Low/Medium/High scale.

| Risk | L | I | Mitigation |
| --- | --- | --- | --- |
| Scope creep — too many features attempted | High | High | Strict MoSCoW discipline; Won’t-Have list is enforced; new ideas go to the backlog, not the sprint. |
| OCR accuracy too low on varied student cards | Medium | High | Early OCR stress-testing; fallback to manual verification; narrow the supported card set for the pilot. |
| Backend / frontend integration drift | Medium | High | Shared API contract agreed early; weekly integration check; contract tests. |
| Team-member availability (exams, illness) | Medium | Medium | Cross-documentation of each module; no single point of knowledge; buffer time in Sprint 3. |
| Cerfa PDF does not satisfy accountants | Medium | High | Validate the generated document early with a real accountant; iterate before the pilot. |
| Pilot zone has too few bakeries | Medium | High | Choose the zone on bakery density; have a backup zone identified. |

# 7. Monitoring Progress

## 7.1 Project Indicators

Progress is tracked with a small, honest set of indicators reviewed at every sprint review:

- Sprint burndown — planned vs. completed backlog items.

- Must-Have completion rate — the MVP must be complete before Should-Haves are started.

- Defect count — open bugs, especially on the QR and tax flows.

- Integration health — does the latest app build work against the latest backend?

## 7.2 Change Indicators

Because the change track runs in parallel, it is monitored too:

- Number of pioneer bakeries signed vs. target.

- Number of verified students in the pilot zone.

- Number of completed donations during the pilot.

- Baker and student satisfaction (short surveys at the pilot review).

## 7.3 Definition of Done

A backlog item is “done” only when all of the following hold:

- The code is reviewed and merged to the main branch.

- It works in an integrated build (app + backend together).

- It has been tested against its acceptance criteria.

- Any user-facing or legal-sensitive behaviour (QR, tax, ID handling) is verified against the project’s legal and security requirements.

# 8. Milestone 2 Deliverables & Transition to Milestone 3

By the end of Milestone 2 the project should be able to demonstrate:

- A documented Agile / Scrum methodology adapted to the team.

- A clear team organisation with roles, governance and decision rules.

- A three-sprint roadmap covering both the build track and the change track.

- A controlled pilot-rollout plan with phases and exit criteria.

- A delivery risk register and a set of monitoring indicators.

Milestone 3 then takes the working pilot and asks how the change is made long-lasting: how adoption is sustained, how Vif scales beyond the pilot zone, how it remains financially viable, and what its long-term vision is.